## Data
Id | Summary | Level 1 | level 1 status | Level 2 | level 2 status | Level 3 | level 3 status | Team | outward Links | inward Links | Assignee | Estimate | IssueType | Key | OriginalEstimate | Reporter | Status | Summary | TimeTracking2
PV | Evaluate Program I | PROG-6 Evaluate Program I | FORECAST |  |  |  |  | UNASSIGNED | 0 | 0 | kuba bielawski |  |  | PV |  | Unassigned |  | Evaluate Program I
PV-31 | Develop a project plan | PROG-6 Evaluate Program I | FORECAST |  |  |  |  | Team Android | 1 | 0 | kuba bielawski | 0m | Story | PV-31 | 2d | kuba bielawski | To Do | Develop a project plan | 0%
PV-32 | Establish a project schedule | PROG-6 Evaluate Program I | FORECAST |  |  |  |  | Team Android | 1 | 1 | kuba bielawski | 0m | Story | PV-32 | 3d | kuba bielawski | To Do | Establish a project schedule | 0%
PV-33 | Lead and manage the project team | PROG-6 Evaluate Program I | FORECAST |  |  |  |  | Team Android | 0 | 1 | kuba bielawski | 0m | Story | PV-33 | 4d | kuba bielawski | To Do | Lead and manage the project team | 0%
PV-34 | Analysis | PROG-6 Evaluate Program I | FORECAST |  |  |  |  | Team Android | 0 | 0 | kuba bielawski | 0m | Story | PV-34 | 1w | kuba bielawski | To Do | Analysis | 0%
PV-29 | Project plan | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 0 | 0 | kuba bielawski | 0m | Story | PV-29 | 0m | kuba bielawski | To Do | Project plan | 0%
PV-30 | Project Management | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 0 | 0 | kuba bielawski | 0m | Story | PV-30 | 1d | kuba bielawski | To Do | Project Management | 0%
PV-35 | Assist in defining the project | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 1 | 0 | kuba bielawski | 0m | Story | PV-35 | 1w 1d | kuba bielawski | To Do | Assist in defining the project | 0%
PV-36 | Gather requirements from business units or users | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 1 | 1 | kuba bielawski | 0m | Story | PV-36 | 1w 2d | kuba bielawski | To Do | Gather requirements from business units or users | 0%
PV-37 | Verify that project deliverables meet the requirements | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 1 | 1 | kuba bielawski | 0m | Story | PV-37 | 1w 3d | kuba bielawski | To Do | Verify that project deliverables meet the requirements | 0%
PV-38 | milestone - Document technical and business requirements | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 0 | 1 | kuba bielawski | 0m | Story | PV-38 | 1w 4d | kuba bielawski | To Do | milestone - Document technical and business requirements | 0%
PV-1 | Architecture and development | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 1 | 0 | kuba bielawski | 0m | Story | PV-1 | 2w | kuba bielawski | To Do | Architecture and development | 0%
PV-2 | [Feature] Tracking and registering GPS data | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 0 | 0 | kuba bielawski | 0m | Story | PV-2 | 2w | kuba bielawski | To Do | [Feature] Tracking and registering GPS data | 0%
PV-18 | [Feature] Enhanced reporting | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 0 | 0 | kuba bielawski | 0m | Story | PV-18 | 2w | kuba bielawski | To Do | [Feature] Enhanced reporting | 0%
PV-20 | Testing | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 0 | 0 | kuba bielawski | 0m | Story | PV-20 | 2w | kuba bielawski | To Do | Testing | 0%
PV-21 | Configuring, using, and managing test environments and test data | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 0 | 1 | kuba bielawski | 0m | Story | PV-21 | 2w | kuba bielawski | To Do | Configuring, using, and managing test environments and test data | 0%
PV-22 | Measuring and reporting test coverage | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 1 | 0 | kuba bielawski | 0m | Story | PV-22 | 2w | kuba bielawski | To Do | Measuring and reporting test coverage | 0%
PV-23 | Architecture | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 0 | 0 | kuba bielawski | 0m | Story | PV-23 | 2w | kuba bielawski | To Do | Architecture | 0%
PV-24 | Picking & executing the right modelling | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 1 | 0 | kuba bielawski | 0m | Story | PV-24 | 2w | kuba bielawski | To Do | Picking & executing the right modelling | 0%
PV-25 | Understand and plan for evolutionary paths | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 1 | 1 | kuba bielawski | 0m | Story | PV-25 | 2w | kuba bielawski | To Do | Understand and plan for evolutionary paths | 0%
PV-26 | Identify and interact with stakeholders | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 0 | 1 | kuba bielawski | 0m | Story | PV-26 | 2w | kuba bielawski | To Do | Identify and interact with stakeholders | 0%
PV-27 | Operations | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 0 | 0 | kuba bielawski | 0m | Story | PV-27 | 2w | kuba bielawski | To Do | Operations | 0%
PV-28 | Planning and controlling of change, resources and deadlines | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Android | 0 | 1 | kuba bielawski | 0m | Story | PV-28 | 2w | kuba bielawski | To Do | Planning and controlling of change, resources and deadlines | 0%
PV-6 | [Feature] Visualization of tracks on a map | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team iOS | 0 | 0 | kuba bielawski | 0m | Story | PV-6 | 2w | kuba bielawski | To Do | [Feature] Visualization of tracks on a map | 0%
PV-8 | [Feature] Training log | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST |  |  | Team Web | 0 | 0 | kuba bielawski | 0m | Story | PV-8 | 2w | kuba bielawski | To Do | [Feature] Training log | 0%
PV-3 | [Story] Tracking GPS data | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST | ITER-38 Iteration1 | FORECAST | UNASSIGNED | 2 | 0 | kuba bielawski | 0m | Story | PV-3 | 2w | kuba bielawski | To Do | [Story] Tracking GPS data | 0%
PV-4 | [Story] Storing GPS data locally | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST | ITER-38 Iteration1 | FORECAST | UNASSIGNED | 0 | 1 | kuba bielawski | 0m | Story | PV-4 | 2w | kuba bielawski | To Do | [Story] Storing GPS data locally | 0%
PV-5 | [Story] Simple UI (start, stop, pause) | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST | ITER-39 Iteration2 | FORECAST | Team Android | 0 | 1 | kuba bielawski | 0m | Story | PV-5 | 2w | kuba bielawski | To Do | [Story] Simple UI (start, stop, pause) | 0%
PV-7 | [Story] Track visualization on a map | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST | ITER-40 Iteration3 | FORECAST | Team iOS | 0 | 0 | kuba bielawski | 0m | Story | PV-7 | 2w | kuba bielawski | To Do | [Story] Track visualization on a map | 0%
PV-9 | [Story] Training log pages | PROG-6 Evaluate Program I | FORECAST | PI-14 PI1 | FORECAST | ITER-40 Iteration3 | FORECAST | Team iOS | 0 | 0 | kuba bielawski | 0m | Story | PV-9 | 2w | kuba bielawski | To Do | [Story] Training log pages | 0%
PV-13 | [Feature] Self-learning algorithm for running | PROG-6 Evaluate Program I | FORECAST | PI-15 PI2 | FORECAST |  |  | Team Android | 0 | 0 | kuba bielawski | 0m | Story | PV-13 | 2w | kuba bielawski | To Do | [Feature] Self-learning algorithm for running | 0%
PV-10 | [Feature] Self-learning algorithm for identifying activity type | PROG-6 Evaluate Program I | FORECAST | PI-15 PI2 | FORECAST |  |  | Team iOS | 0 | 0 | kuba bielawski | 0m | Story | PV-10 | 2w | kuba bielawski | To Do | [Feature] Self-learning algorithm for identifying activity type | 0%
PV-16 | [Feature] Support for cycling, walking and interval training | PROG-6 Evaluate Program I | FORECAST | PI-15 PI2 | FORECAST |  |  | Team Web | 0 | 0 | kuba bielawski | 0m | Story | PV-16 | 2w | kuba bielawski | To Do | [Feature] Support for cycling, walking and interval training | 0%
PV-11 | [Story] Notify user about identified activity type | PROG-6 Evaluate Program I | FORECAST | PI-15 PI2 | FORECAST | ITER-41 Iteration4 | FORECAST | UNASSIGNED | 0 | 0 | kuba bielawski | 0m | Story | PV-11 | 2w | kuba bielawski | To Do | [Story] Notify user about identified activity type | 0%
PV-12 | [Story] Sound cues for activity type switch | PROG-6 Evaluate Program I | FORECAST | PI-15 PI2 | FORECAST | ITER-41 Iteration4 | FORECAST | Team Android | 0 | 0 | kuba bielawski | 0m | Story | PV-12 | 2w | kuba bielawski | To Do | [Story] Sound cues for activity type switch | 0%
PV-15 | [Story] Get user confirmation on the activity type | PROG-6 Evaluate Program I | FORECAST | PI-15 PI2 | FORECAST | ITER-42 Iteration5 | FORECAST | UNASSIGNED | 0 | 0 | kuba bielawski | 0m | Story | PV-15 | 2w | kuba bielawski | To Do | [Story] Get user confirmation on the activity type | 0%
PV-19 | [Story] Enhanced track information (elevation, max speed, pace etc.) | PROG-6 Evaluate Program I | FORECAST | PI-15 PI2 | FORECAST | ITER-42 Iteration5 | FORECAST | Team iOS | 0 | 0 | kuba bielawski | 0m | Story | PV-19 | 2w | kuba bielawski | To Do | [Story] Enhanced track information (elevation, max speed, pace etc.) | 0%
PV-17 | [Story] Step count for walking | PROG-6 Evaluate Program I | FORECAST | PI-15 PI2 | FORECAST | ITER-42 Iteration5 | FORECAST | Team Web | 0 | 0 | kuba bielawski | 0m | Story | PV-17 | 2w | kuba bielawski | To Do | [Story] Step count for walking | 0%
PV-14 | [Story] Step count for running | PROG-6 Evaluate Program I | FORECAST | PI-15 PI2 | FORECAST | ITER-43 Iteration6 | FORECAST | Team Android | 0 | 0 | kuba bielawski | 0m | Story | PV-14 | 2w | kuba bielawski | To Do | [Story] Step count for running | 0%

## Pivot table - assignment
level 2 status | (All)
level 3 status | (All)
Count of Id | Column Labels
| (blank) | (blank) Total | Grand Total
Row Labels | (blank)
(blank)
(blank)
Grand Total